## Table 1
Final Bill Payment Pending as on 28.05.2021 -RD Works
Sl.No | District Name | Pending More than 6 months | Nov-20 | Dec-20 | Jan-21 | Feb-21 | Mar-21 | Apr-21 | May-21 | Total
1 | Ariyalur | [8 empty] | 0
2 | Chengalpet | [8 empty] | 0
3 | Coimbatore |  |  |  | 1 | 1 | 7 | 3 |  | 12
4 | Cuddalore |  |  |  |  | 1 |  |  |  | 1
5 | Dharmapuri |  |  | 1 |  | 1 | 1 | 2 | 1 | 6
6 | Dindigul | 1 |  |  |  | 1 | 3 |  |  | 5
7 | Erode | 1 |  |  | 2 |  |  |  |  | 2
8 | Karur | 1 |  |  |  | 2 | 2 | 4 | 1 | 10
9 | Kallakuruchi | [6 empty] | 1 |  | 1
10 | Krishnagiri |  |  | 2 |  |  | 1 | 3 |  | 6
11 | Madurai | [5 empty] | 1 |  |  | 1
12 | Namakkal |  |  | 7 |  | 4 | 3 | 5 |  | 19
13 | Pudukkottai |  |  |  |  | 1 |  |  |  | 1
14 | Salem |  |  |  |  | 1 |  |  |  | 1
15 | Sivagangai | 1 |  | 1 |  | 1 |  | 1 |  | 4
16 | The Nilgiris | 2 | 2 | 3 | [5 empty] | 5
17 | Tirunelveli | [6 empty] | 1 |  | 1
18 | Tenkasi | [6 empty] | 1 |  | 1
19 | Tiruppur | [7 empty] | 2 | 2
20 | Tiruvarur |  |  | 1 | 8 | 4 | 5 | 5 | 1 | 24
| Grand Total | 6 | 2 | 15 | 11 | 17 | 23 | 26 | 5 | 104
Details of 5 Works
1) Erode district-Gobi block-PMGSY-III work -final payment made, still it is displayed in pending List -Issue raised to OMMAS team, 2) PMGSY Phase XI work (Forest) -T08-Thamaraikarai to Kongadai road - graded as "U"
3) Sivagangai -It is a bridge work, executed by the same contractor who also executed the road work, Payment has been made which includes the expenditure for both road and bridge work, Issue has been addressed to OMMAS team
4) Dindigul, 5) Karur -PMGSY-III works -Initially Option to select "Final Payment as Yes" was not enabled in payment module. Hence dummy payments has to be made.